## Sheet1
| Date | Tasks | Time (duration)
1 | 20/03/2018 | Arduino tutorials | 3
Basic tutorials
Basic connections
LED, button,..
Tests on basic scripts
2 | 21/03/2018 | NRF module tutorial | 3
NRF module test
NRF maniacbug library
3 | 22/03/2018 | NRF module review | 3
NRF module test 2
Multiple NRF module connect
Multiple NRF tutorial
4 | 23/03/2018 | Multiple NRF tutorial | 3
Connecting multiple NRF
5 | 24/03/2018 | Connecting multiple NRF | 3
Testing multiple NRF
Testing 2 slaves with one master
6 | 25/03/2018 | Testing failed with 2 slaves | 3
Reviewing other libraries for NRF
Testing RF24 network
7 | 26/03/2018 | Checking modifications required on NRF | 3
NRF 24 mesh library compatible with mod
Checking NRF 24 mesh library
8 | 27/03/2018 | NRF 24 mesh library | 3
Checking parts of program
Creating documentation
9 | 28/03/2018 | Creating documentation | 3
Testing NRF 24 mesh with multiple NRF
Testing 24 mesh
10 | 29/03/2018 | Connection stable with 2 NRF | 3
Testing different packages
Creating clicker package
11 | 30/03/2018 | Error sending some packages | 3
Creating structure
Sending structure packages
12 | 2018-01-04 | Creating symbiot id | 3
Purchase of various other modules
NodeMCU + SD
13 | 2018-02-04 | Creating clicker buttons | 3
Testing buttons
Testing LED
Creating logic with button pressed and answer
Error in clicking button
14 | 2018-03-04 | Source of error - connection problem with ground | 3
Testing button logic
Combine with NRF packages and answer
15 | 2018-04-04 | Debuggin error in packages | 3
Acknowledge packet error
Correcting error (event based)
16 | 2018-05-04 | Packages working (review and test) | 3
Bolt register
Bolt tutorial
Bolt local variable not responsive
17 | 2018-05-04 | API bolt calls confusing (shift to nodemcu) | 3
NodeMCU tutorials
NodeMCU local IP + button test
18 | 2018-06-04 | Connecting SD card module to nodemcu + arduino | 3
Debugging for error
Connecting connection
19 | 2018-07-04 | Shit to bolt (Due to errors + complete website based app) | 3
API calls debug
Serial communication established
Testing serial data
20 | 2018-08-04 | Unable to pull data into website from serial data | 3
Debugging API calls
Scheduled call with BOLT
Mail to BOLT
Unable to solve the API call
21 | 2018-09-04 | Mukunth + sandeep pulling data into usable format | 3
Simulatneously working with NODEMCU
Package transfer to local IP
22 | 2018-10-04 | Working with bolt (different WIFI) | 3
Connection fail with local WIFI
Changing ownership rights of BOLT
Linking bolt with local id + connection
Connection failed
Totak |  |  | 66